## ACA Project Master Schedule
ADAPTIVE CONTINUOUS AUTHENTICATION (ACA) - UCS503P PROJECT SCHEDULE
TIET Patiala • Supervisor: Prof. Asif • Yatharth Kansal, Anjali Kumari, Ridhi Batra
Task ID | Phase & Task Name | Assigned Lead | Start Date | End Date | Duration (Days) | Dependencies | Status | Progress (%) | Deliverable / Output | Course Milestone
Phase 1: Problem Formulation & Threat Modeling [Week 1-2]
T01 | Literature Review on Keystroke Behavioral Biometrics | Yatharth K. | 2026-08-01 | 2026-08-05 | 5 | None | Completed | 100 | Research Notes & Taxonomy | Proposal
T02 | Threat Modeling: Workstation Hijacking & Token Theft | Yatharth K. | 2026-08-06 | 2026-08-09 | 4 | T01 | Completed | 100 | Attack Vectors & Scenarios | Proposal
T03 | Project Criteria Justification & Scope Definition | Anjali K. | 2026-08-10 | 2026-08-12 | 3 | T02 | Completed | 100 | criteria-for-selection.md | Proposal
T04 | Formal LaTeX Proposal Document & Compilation | Ridhi B. | 2026-08-13 | 2026-08-16 | 4 | T03 | Completed | 100 | main.pdf (Proposal) | Milestone 1
Phase 2: Hardware & DOM Keystroke Collection Engine [Week 2-3]
T05 | OS-Level Global Keystroke Listener (pynput) | Yatharth K. | 2026-08-17 | 2026-08-21 | 5 | T04 | Completed | 100 | keyboard_logger.py | Prototype
T06 | Client-Side Ephemeral HMAC-SHA256 Key Anonymizer | Yatharth K. | 2026-08-22 | 2026-08-24 | 3 | T05 | Completed | 100 | Zero-Logging Security Layer | Prototype
T07 | Initial User Behavioral Baseline Collection (U01/S01, S02) | Yatharth K. | 2026-08-25 | 2026-08-28 | 4 | T06 | Completed | 100 | data/raw/own/U01/ | Prototype
T08 | Path Traversal & Security Validation Protocols | Ridhi B. | 2026-08-29 | 2026-08-31 | 3 | T07 | Completed | 100 | Security Hardening | Prototype
Phase 3: Biometric Feature Engineering & ML Pipeline [Week 4-5]
T09 | Hold (Dwell) and Flight Timing Calculation Algorithms | Yatharth K. | 2026-09-01 | 2026-09-03 | 3 | T08 | Completed | 100 | keystroke_features.py | Prototype
T10 | 10-Second Sliding Behavioral Window Aggregator | Yatharth K. | 2026-09-04 | 2026-09-06 | 3 | T09 | Completed | 100 | keyboard_window_features.csv | Prototype
T11 | Inactive Window Gating Policy (Min. 5 Keystrokes) | Anjali K. | 2026-09-07 | 2026-09-08 | 2 | T10 | Completed | 100 | Idle Leniency Logic | Prototype
T12 | Scikit-Learn Preprocessing Pipeline (Imputer + Scaler) | Yatharth K. | 2026-09-08 | 2026-09-09 | 2 | T10 | Completed | 100 | SimpleImputer, StandardScaler | Prototype
T13 | Isolation Forest Anomaly Model Training & Persistence | Yatharth K. | 2026-09-09 | 2026-09-10 | 2 | T12 | Completed | 100 | anomaly_model.pkl | Milestone 2
T14 | Continuous Linear Trust-Mapping Mathematical Formula | Yatharth K. | 2026-09-10 | 2026-09-11 | 2 | T13 | Completed | 100 | trust_score.py (0-100) | Milestone 2
Phase 4: Web Dashboard & Real-Time Decision Integration [Week 5-6]
T15 | Flask REST API Gateway & Authentication Routes | Yatharth K. | 2026-09-11 | 2026-09-12 | 2 | T14 | Completed | 100 | main.py, auth.py | Prototype
T16 | Responsive Security Cockpit Dark-Mode UI | Anjali K. | 2026-09-12 | 2026-09-13 | 2 | T15 | Completed | 100 | dashboard.html, style.css | Prototype
T17 | Real-Time Dynamic SVG Gauge & Live Historical Chart | Anjali K. | 2026-09-13 | 2026-09-14 | 2 | T16 | Completed | 100 | dashboard.js (SVG renderer) | Prototype
T18 | Dynamic 3-Tier Policy State Machine (ALLOW, VERIFY, LOCK) | Yatharth K. | 2026-09-14 | 2026-09-15 | 2 | T17 | Completed | 100 | decision.py | Milestone 3
T19 | Replay Mode Controller for Ground-Truth Demonstrations | Yatharth K. | 2026-09-15 | 2026-09-16 | 2 | T18 | Completed | 100 | Engine Replay Mode | Prototype
Phase 5: Automated Testing, Benchmarking & Deliverables [Week 6-7]
T20 | Automated Integration Test Suite (11 Tests) | Ridhi B. | 2026-09-16 | 2026-09-17 | 2 | T19 | Completed | 100 | code/tests/ (100% Pass) | Prototype
T21 | Latency & Performance Engineering Benchmarking | Yatharth K. | 2026-09-17 | 2026-09-18 | 2 | T20 | Completed | 100 | Benchmark Tables (0.8ms) | Prototype
T22 | Mid-Semester Prototype LaTeX Report & Vector Diagrams | Ridhi B. | 2026-09-18 | 2026-09-19 | 2 | T21 | Completed | 100 | Report PDF + 4 Diagrams | Milestone 4
T23 | Presentation Deck & Live Demonstration Rehearsal | Anjali K. | 2026-09-19 | 2026-09-20 | 2 | T22 | Completed | 100 | Adaptive_Continuous_Auth.pptx | Milestone 4