## Gantt Chart
Adaptive Continuous Authentication — Gantt Chart
Edit Start / End week (1–6); timeline bars recalculate in Excel.
Weeks 1–3 are indicative retrospective allocations; Weeks 4–6 are plans.
ID | Task | Start week | End week | Status | Dependencies | 1 | 2 | 3 | 4 | 5 | 6
T01 | Requirements and project scope | 1 | 1 | Completed | — | 1 | 0 | 0 | 0 | 0 | 0
T02 | Proposal and system design | 1 | 2 | Completed | T01 | 1 | 1 | 0 | 0 | 0 | 0
T03 | Keyboard event collector | 1 | 1 | Completed | T01 | 1 | 0 | 0 | 0 | 0 | 0
T04 | HMAC identifiers and protected storage | 1 | 1 | Completed | T03 | 1 | 0 | 0 | 0 | 0 | 0
T05 | Hold / flight timing extraction | 1 | 1 | Completed | T04 | 1 | 0 | 0 | 0 | 0 | 0
T06 | 10-second windows and activity flag | 1 | 1 | Completed | T05 | 1 | 0 | 0 | 0 | 0 | 0
T07 | Level 0 / Level 1 and use-case diagrams | 2 | 2 | Completed | T02 | 0 | 1 | 0 | 0 | 0 | 0
T08 | Project presentation | 2 | 2 | Completed | T02 | 0 | 1 | 0 | 0 | 0 | 0
T09 | Isolation Forest pipeline | 3 | 3 | Completed | T06 | 0 | 0 | 1 | 0 | 0 | 0
T10 | Trust mapping and decision engine | 3 | 3 | Completed | T09 | 0 | 0 | 1 | 0 | 0 | 0
T11 | Flask dashboard and live capture | 3 | 3 | Completed | T10 | 0 | 0 | 1 | 0 | 0 | 0
T12 | Replay and integration checks | 3 | 3 | Completed | T11 | 0 | 0 | 1 | 0 | 0 | 0
T13 | Revised proposal, Level 2 DFD and schedule | 3 | 3 | Completed | T07,T10 | 0 | 0 | 1 | 0 | 0 | 0
T14 | Additional users and recording sessions | 4 | 4 | Planned | T12 | 0 | 0 | 0 | 2 | 0 | 0
T15 | Feature quality and held-out session split | 4 | 4 | Planned | T14 | 0 | 0 | 0 | 2 | 0 | 0
T16 | Retrain and evaluate baseline | 5 | 5 | Planned | T15 | 0 | 0 | 0 | 0 | 2 | 0
T17 | Takeover trials and threshold review | 5 | 5 | Planned | T16 | 0 | 0 | 0 | 0 | 2 | 0
T18 | Latency and false-accept / reject report | 5 | 6 | Planned | T17 | 0 | 0 | 0 | 0 | 2 | 2
T19 | Final report and slide update | 6 | 6 | Planned | T18 | 0 | 0 | 0 | 0 | 0 | 2
T20 | Demo rehearsal and submission preparation | 6 | 6 | Planned | T19 | 0 | 0 | 0 | 0 | 0 | 2

## Notes
Schedule notes
Scope | Keyboard-only course prototype; no new model performance is claimed.
Week basis | Six relative weeks follow the journal sequence; calendar dates are not assumed.
Completed | Existing artifact or implementation is present; week allocation is indicative.
Planned | Future work; replace with actual dates/status as it happens.
Dependencies | Task IDs are sequencing guidance; same-week tasks may occur sequentially.
Reference | https://github.com/NamanArora2709/ucs503p-202627-privalens
Reference access | Repository lists a Gantt workbook; individual file could not be retrieved.
Legend | Green = completed; blue = planned.
Editing | Change columns C/D and status Completed or Planned; formula cells recalculate.
Preview | Regenerate SVG/CSV/workbook from docs/tools/generate_planning_assets.py; generation overwrites workbook edits.